## All Tasks and Activities
Use Case |  | Description | Additional information | Tasks involved | Remarks
User Accounts
A1 |  | open the formulary without any login additional to my network login |  | configuration for logging intranet user.
A2 |  | Stipulate: who can make edits for approval (FEs) and who can approve edits or make edits directly without seeking approval (FPs) assigning user name + password logins for these roles |  | UI screen for handling username and password | refer to Stories for "Admin Module" row #101
C1 | FM | brand our local formulary, by: inserting our logo (up to 265 pixels wide by up to 32 pixels deep) on every page |  | logic to choose logo to display |  | 20
C2 | FM | brand our local formulary, by: renaming the BNF and BNFC catalogs with local formulary names if we wish |  | display local names
C3 | FM | prominently post up-to-the-minute announcements of drug recalls that all our pharmacists will see, by: choosing an RSS feed for the home page |  | Integrate RSS feed
C4 | FM | prominently post important notices for prescribers on the home page |  | Display static data
C5 | FM | build up a library of local guidance through the addition of records to the Documents catalog root on the home page |  | Display static data
C6 | FM | hide BNFC (e.g. as we've never added applicable notes to it) or even the BNF (if we’re purely a children’s hospital trust) |  | logic to hide/unhide BFC/BNFC tab
C7 | FM | include my contact details so that staff questions come to me |  | display contact details
C8 | FM | implement our own formulary status nomenclature by adding or changing status identifiers: up to ten statuses to be specifiable by name, color code and single-letter abbreviation to use as marker* |  | This story deals with just displaying the status.
Search Module
I1 | PD | search all three catalogs or just one formulary |  | Search on drug name (within a formulary, or for All data)
I2 | PD | search within a formulary just on BNF (or BNFC) drug records |  | Search on interactions
I3 | PD | find information on a drug whose name I can spell only approximately - by entering two letters and choosing the full name from a dropdown list |  | UI changes to display drug name when user enters just 2 characters
I4 | PD | easily navigate to drug information categorized by its therapeutic area, especially where a drug substance has different uses* |  | display drug information
I5 | PD | see the local formulary status and locally added instructions above the BNF/BNFC content of record pages |  | display status and instructions above BNF/BNFC content
I6 | PD | see the local formulary status flags whenever I look at the expandable ToC, the related information lists or the search results |  | display ToC
I7 | PD | find a summary of the potential interactions of a drug by calling up a table of the BNF information for all interactant pairs in which it occurs as one of the elements |  | display interactions
I8 | PD | be signposted to further information about drugs of the same class and about related drugs when viewing a drug record |  | display more info about drugs of same class and related drugs
I9 | PD | be alerted to specific information on drugs for use in children when I’m in the adult formulary, and vice versa - by being offered separate expandable lists of related records for the two formularies |  | display alert
I11 | PD | be alerted when a NICE TA† applies by a prominent link to the BNF summary |  | display NICE TA alert link and open an external link
I12 | PD | read an applicable NICE TA in full by opening an external hyperlink from the BNF summary in another tab
I13 | PhPP | ensure that users can access the record for a drug (if it is described in the BNF or BNFC) by entering its DM+D identifier‡ |  | Separate URL creation and display | The database includes the substance identifiers (ID) from the NHS Dictionary of Medicines and Devices (dm+d). To find a drug from its dm+d ID, it is necessary to enter the path into the address bar of your browser, as though you were going to another website. The address (URL) is constituted as follows: http://localservername:portnumber/bnf/dmd/ID
Edit the content: formulary status
F1 | ≥FE | set a flag on a drug so as to assign it a status in our local formulary |  | Ability to set the flag,
F2 | ≥FE | change the status flag attached to a drug in our local formulary |  | change and remove status
F3 | ≥FE | remove the status flag attached to a drug in our local formulary |  | submit status for approval
F4 | FE | submit my status assignment for approval |  | (Approval functionality)
F5 | ≥FP | have the option of publishing my status assignment/change immediately if I don’t want to seek approval |  | Publish immediately
Edit the content: individual record notes (Annotations)
E1 | ≥FE | add a note to a record |  | Adding a note, Apply formatting, Amending note
E2 | ≥FE | amend the text of a note in a record |  | preview text
E3 | ≥FE | refer to the previous versions of a record when I’m editing a note |  | previous versions
E4 | ≥FE | apply simple formatting to the text of a note in a record – bold/italic/underlined; font size; font color; highlighting; list indentation; range left/right/centre and be able to insert web links |  | Submit for approval (Approval functionality)
E5 | ≥FE | see how a record will look when the edits are published |  | preview document
E6 | FE | submit my created/edited note for approval |  | Submit for Deletion
E7 | ≥FP | have the option of publishing my created/edited note immediately if I don’t want to seek approval |  | Publish immediately
E8 | FE | submit an entire note deletion instruction for approval | deletion from LIVE site | submit an entire note deletion instruction for approval
E9 | ≥FP | have the option of deleting a note immediately if I don’t want to seek approval |  | delete immediately
Edit the content: nodes
E11 | ≥FE | append a placeholder (blank) record to a BNF/BNFC chapter or section,* or insert one in the local Documents |  | Create a node as a place-holder
E12 | ≥FE | reorder records appended to a BNF/BNFC chapter or section, or in the local Documents |  | Appending the node, renaming , deleting the records
E13 | ≥FE | rename my own or colleagues' records
E14 | ≥FE | delete my own or colleagues' records
Edit the content: reusable snippets
E16 | ≥FE | create a content item with a title and text and insert it into one record or an ad-hoc group of records |  | creating, amending, removing or inserting a content
E17 | ≥FE | be certain that when I insert or amend a content item I'm in the right context, or covering the intended instances, if the drug is the subject (and/or title) of more than one record in the database
E18 | ≥FE | insert a content item into further records
E19 | ≥FE | remove a content item from one or more records
E20 | ≥FE | amend the text of a content item
E21 | ≥FE | see earlier versions of an edited content item |  | View earlier versions
E22 | ≥FE | apply simple formatting to the text of a content item
E23 | ≥FE | include an external link or links in a content item in one record or an ad-hoc group of records |  | including and deleting external link
E24 | ≥FE | delete an external link from a content item
E25 | ≥FE | attach a local file or files to a content item in one record or an ad-hoc group of records |  | Attach or remove local file
E26 | ≥FE | remove a local file attachment from a content item
E27 | ≥FE | save a half-done content item for completion later |  | saving draft version
E28 | ≥FE | reopen and continue work on a half-done content item |  | working over a draft version
E29 | FE | submit my created/edited content item for approval |  | Approval , deletion, approve immediately for created/edited content
E30 | ≥FP | have the option of publishing my created/edited content item immediately if I don’t want to seek approval
E31 | FE | submit a content item deletion instruction for approval
E32 | ≥FP | have the option of deleting a content item immediately if I don’t want to seek approval
Monitor content changes: approval/workflow
R1 | ≥FP | see a list of edits awaiting review |  | view list and approve/reject or delete or mark for further attention
R2 | ≥FP | publish proposed editorial changes or reject them either by cancelling or by marking as in need of further attention – or even delete the whole content item
R3 | ≥FP | publish proposed formulary status changes or reject them by cancelling - or leave unapproved
R4 | ≥FP | compare the submitted redraft of content with the current, unamended version |  | comparison
R5 | ≥FP | access all previous versions of any edited content item |  | access previous content
R6 | ≥FP | see where content attached to more than one record is used |  | Need to display links where content matches other records
R7 | ≥FP | be warned before deleting content that is attached to additional records |  | warning before deletion
Monitor content changes: audit
R8 | ≥FP | trace who made a particular content change, and when |  | Identifying the changed content (search ). Identifying who changed for particular content or reusable content and when. User might be required to see where all reusable content is required.
R9 | ≥FP | identify who changed the record associations of a reusable content item, and when
R10 | ≥FP | select individual editors' activity for review by filtering an audit trail |  | individual activity audit
R11 | ≥FP | review overall editing activity in an audit trail filterable on formulary, type of content and publishing action |  | another search on basis of parameters to review overall editing activity
R12 | FM | check* whether BNF editorial updates have affected the occurrence and visibility of any of our local content |  | Need more info on what report is required here,
R13 | FM | view records that have been deleted in an archive |  | view deleted records
Export formulary content
X1 | FM | run formulary reports for publication showing the status of drugs in alphabetical order or in BNF taxonomy order choose which formulary choose which statuses to include choose whether or not to include our notes choose output as tabbed text, HTML or PDF select individual chapters or whole formulary | This is a complex single report. All variations are generated depending on choice of input parameter/s | Generation of report (refer section above) output to be as per the chosen parameters.
X2 | FM, | show how our local formulary complies with NICE Guidance on Local Formularies- by optionally including TA links in the report as well as status (with or without our notes)
X3 | FM | use the same functionality to run internal reports, e.g. listing which drugs in the BNF we have included in our formulary or consciously excluded from it or not yet decided on |  | Run internal reports
X4 | PD | Print out individual records- from browser |  | Provision to print
Other/miscellaneous requirements
O1 | ITM | obtain positive confirmation that an upgrade has run successfully
O2 | PhPP | supply the database contained in the basic installer such that there are three default formulary statuses - On Formulary = green, Restricted = amber and Off Formulary = red – of which the last two are not yet associated with any drugs, but any drug therapy recommended in a NICE TA is marked as “On Formulary”
O3 | PhPP | ensure that accented letters, Greek letters, mathematical symbols etc, whether in the BNF or in locally created content, display with the correct grapheme in all outputs
Admin Module
|  | Manage Publishing Queue |  | Integration | Integration with existing module for publisher
Create/Edit local Content
|  | Manage Formulary | The Manage Formulary admin screen allows the BNF and BNFC to be renamed when you adapt them to create your own local formulary. | Creation of screen. Testing impact on home page
|  | Manage Formulary Status | The Formulary Status admin screen allows the name, color code and abbreviation for up to six statuses to be determined locally. | Managing Reference Data
Manage Users
|  | Manage RSS feeds |  |  | Configuring RSS Feeds.
Total (days)

## Revised Plan
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20
Sprint 0 | [17 empty] | GO LIVE
Setting up environment Tools for testing, coding, integrating and building are set up Completion of conceptual design Build Environment set up and tested. Other Sprint 0 Activities |  | Sprint 1 |  |  |  | UAT
|  | UI Mock ups and Feedback Coding and Unit Testing Automated Unit testing System testing |  |  | Sprint 2 |  |  | Sprint 3 Stabilizing Sprint |  | Sprint 4 |  |  | Sprint 5 |  |  | Sprint 6
[5 empty] | UI Mock ups and Feedback Coding and Unit Testing Automated Unit testing System testing |  |  |  |  | UI Mock ups and Feedback Coding and Unit Testing Automated Unit testing System testing |  |  | UI Mock ups and Feedback Coding and Unit Testing Automated Unit testing System testing |  |  | UAT Support Remainder of System testing (if any)
System testing Completion of all pending work and closure of defects etc.
Functionality 1. 2. Find drug information. (Partial) 2. Edit content Formulatory Status (James) 3. user Accounts (partial) 4. Edit content: nodes (partial)
[5 empty] | Functionality 1. Edit content: individual record notes 2. Find drug information. (complete) 3. Edit content Formulatory Status (James) 4. User Accounts (complete) 5. Edit content: nodes (complete) |  |  |  |  | Functionality 1. Monitor content changes: audit 2. Export formulary content 3. Other/miscellaneous requirements 4. Admin Module 5. Monitor content changes: approval/workflow |  |  | Functionality 1. Edit content: reusable snippets 2. Drug comparison 3. Annotation Search 4. View changes across BNF versions
Legends
Sprint Activities
Sprint deliverables
Data Migration Development , Testing and Support
UAT

## Sheet4
Reference | Summary of user Story /Work | Owned by | Development Start Date | Development End Date | Deviation (if Any) | Test Start Date | Test End Date | Deviation (if Any) | Status RAG | Remarks
Edit the content: individual record notes (Annotations)
E1 | add a note to a record | Aarti, Abin | 2015-09-18 | 2015-09-23
E2 | amend the text of a note in a record | Aarti, Abin | 2015-09-18 | 2015-09-23
E3 | refer to the previous versions of a record when I’m editing a note | Aarti, Abin | 2015-09-24 | 2015-09-25
E4 | apply simple formatting to the text of a note in a record – bold/italic/underlined; font size; font color; highlighting; list indentation; range left/right/centre and be able to insert web links | Aarti | 2015-09-18 | 2015-09-23
E5 | see how a record will look when the edits are published | Aarti | 2015-09-24 | 2015-09-25
E6 | submit my created/edited note for approval | Aarti, Abin | 2015-09-18 | 2015-09-23
E7 | have the option of publishing my created/edited note immediately if I don’t want to seek approval | Aarti, Abin | 2015-09-28 | 2015-10-01
E8 | submit an entire note deletion instruction for approval | Aarti, Abin | 2015-09-18 | 2015-09-23
E9 | have the option of deleting a note immediately if I don’t want to seek approval | Aarti, Abin
Edit the content: nodes
E11 | append a placeholder (blank) record to a BNF/BNFC chapter or section,* or insert one in the local Documents | Aarti, Abin | 2015-09-28 | 2015-10-01
E13 | rename my own or colleagues' records | Aarti, Abin | 2015-09-28 | 2015-10-01
E14 | delete my own or colleagues' records | Aarti, Abin | 2015-09-28 | 2015-10-01
| submit my created/edited/deleted nodes for approval | Aarti, Abin | 2015-09-28 | 2015-10-01
Search Module
FC 12 and FC 15 | Search for drug | Mohini | 2015-09-21 | 2015-09-24
| Search for Medicinal Product/preparations | Mohini | 2015-09-21 | 2015-09-24
| Search for drug class | Mohini | 2015-09-28 | 2015-09-30
| Search for treatment summaries | Mohini | 2015-09-28 | 2015-09-30
| Grouping of Search results | Mohini | 2015-10-01 | 2015-10-05
Changes to TOC
| Implement Changes to TOC | Ajay, Jitendra | 2015-09-21 | 2015-09-23
Reusable Snippets (excluding targets)
FC-47 | Reusable content creation | Ajay, Abin | 2015-09-24 | 2015-09-28
FC-51 | Reusable content editing | Ajay, Abin | 2015-09-29 | 2015-10-01
FC-52 | Reusable content formatting | Ajay, Abin | 2015-09-29 | 2015-10-02
Rollover from Sprint 1
FC-98 | View BNF records | Jitendra | 2015-09-18 | 2015-09-21
FC-100 | View BNFC Records. | Jitendra | 2015-09-18 | 2015-09-21
FC-20 | Check BNF/BNFC drug against interactions database | Jitendra | 2015-09-18 | 2015-09-21
FC-99 | Find interactions data for a drug from a list in tree view of contents | Jitendra | 2015-09-18 | 2015-09-21
FC-21 | Record pages to include “Related information” links panel | Jitendra | 2015-09-22 | 2015-09-23
FC-22 | “Related information” links to include corresponding records for the same drug in the other formulary | Jitendra | 2015-09-22 | 2015-09-23
FC-18 | On a BNF/BNFC record page any locally added information should be prominent | Jitendra | 2015-09-22 | 2015-09-23
| Defect Closure (Sprint 1) | Jitendra, Web team | 2015-09-18 | 2015-09-21
| Automated unit testing completion for sprint 1 | Jitendra/ Abin | 2015-09-24 | 2015-09-29
Interim release dates