## Slide 1
RPS - Formulary Complete
Sprint 9 Planning

## Slide 2
Agenda
Sprint 9 Deliverables’ Status
Sprint 9 metrics
Sprint 9 Retrospective
Risks & Impact
Questions?

## Slide 3
Sprint 9 – Deliverables’ Status
User story | Summary | Status | Remarks
FC-686 | Admin options displaying when not logged in | delay | 
FC-447 | FC50-Edit note functionality is not working properly. | Done | 
FC-604 | Edit note link not working | In System test | 
FC-602 | Add button for adding notes is unintuitive | In System test | 
FC-592 | Compare differences link still present on view previous version of a record or note page | Done | 
FC-34 | Easily access local content creation to place a note on a record | Done | 

## Slide 4
Sprint 9 – Deliverables’ Status
User story | Summary | Status | Remarks
FC-623 | Approval process error (local note) | Done | 
FC-36 | View previous version of note | In Progress | 
FC-444 | FC-147-Links/documents not getting opened in the records/notes | In System test | 
FC-441 | URL and File upload for Records and Notes | Done | 
FC-57 | Reorder snippets and any note attached to a record |  | Confirmed on local test environment. Needs a deployment on cloud to confirm
FC-693 | Notes should be valid with either a title or content | Done | 

## Slide 5
Sprint 9 – Deliverables’ Status
User story | Summary | Status | Remarks
FC-35 | Amend a note on a record (NB duplicates FC-51) | Test in Progress | 
FC-639 | Add note does not work: (1) publish immediately from admin page | Done | 
FC-640 | Add note does not work: (2) add from monograph page | Done | 
FC-471 | FC- "Delete directly" and "Recommend deletion" buttons are not available on create note page. | Test in Progress | 
FC-641 | Add note does not work: (3) target selector has mind of its own | Test in Progress | 
FC-6 | Option for admin to insert noticeboard and notices on home page |  | 

## Slide 6
Sprint 9 – Deliverables’ Status
User story | Summary | Status | Remarks
FC-5 | RSS feed on home page for drug recalls | In progress | 
FC-586 | FC-438_Editing Formulary Status_Assigned Formulary Status on Thruptic use cannot be deleted. | Done | 
FC-501 | Recommend deletion "approve" button functionality is not working | Done | 
FC-699 | Remove records where status is only change table |  | 
FC-504 | Content not displayed when amended draft record is submitted for approval | Done | 
FC-512 | FC 439-Formulary Status not getting assigned to monograph | Done | 

## Slide 7
Sprint 9 – Deliverables’ Status
User story | Summary | Status | Remarks
FC-515 | Directories - not able to delete a directory - displays internal server error | Done | 
FC-582 | Directories - not able to view the created directories and records in Documents on Home Page under local guidance | Done | 
FC-506 | Manage Users - Users with different associated formularies are displayed within the Manage users list | Done | 
FC-483 | FC-238_Review Changes_Pending Approval Screen Links and Documents are increased each time when click on submitted record for approval and back button. |  | 
FC-479 | FC 147- Records -Able to save a published record as draft for the second time | In Progress | 
FC-418 | No sign in button | Done | 

## Slide 8
Sprint 9 – Deliverables’ Status
User story | Summary | Status | Remarks
FC-417 | Change password link showing for read only users | Done | 
FC-416 | Sign out button for not signed in users | Done | 
FC-148 | Easily access local record content editing page | In Progress, delay | 
FC-70 | Audit trail to include snippet associations |  | 
FC-66 | Reviewer’s options for formulary status changes |  | 
FC-65 | Reviewer’s options for content changes |  | 
FC-41 | Optionally skip ratification stage when deleting a note |  | 

## Slide 9
Sprint 9 – Deliverables’ Status
User story | Summary | Status | Remarks
FC-40 | Local content deletion |  | 
FC-31 | Remove assigned formulary status |  | 
FC-19 | Formulary status marker to accompany drug record title in navigation | In Progress, delay | 
FC-11 | Formulary status options can be edited even if already applied to drug records |  | 
FC-634 | Workflow: Manage Publishing Queue is not the latest approved version | In System Test | 
FC-635 | Workflow: review submission page has duplicate buttons | Done | 
FC-636 | Workflow: Approve record deletion or record amendment not working | Done | 

## Slide 10
Sprint 9 – Deliverables’ Status
User story | Summary | Status | Remarks
FC-679 | No access to status editor from local record page |  | 
FC-685 | Published change to local record not "taking" in live content | Done | 
FC-687 | Welcome back sign not working properly | Done | 
FC-459 | Formulary Status appears to a record if view a record which has formulary status. |  | 
FC-486 | FC-63_View Published Version link is not working as expected while adding a new record. |  | 
FC-475 | Manage Users-New users are not getting displayed in the list | Done | 

## Slide 11
Sprint 9 – Retrospective
  What Worked
    Frequent check-ins, and prompt code reviews
    High level design approval from Ian.
  What can be improved
  Release Process
    James working on this. (Automatic Deployments)
    Development and test environment.
      Two separate environments being created on Cloud (Dev and QA)
    Logging time in JIRA
      Observed improvements, but needs betterment.
    Questions on functionalities to be asked earlier in the sprint.

## Slide 12
Definition of Done
Definition of Done will be the System Test Cases as approved by RPS

## Slide 13
Change Requests
Manage Directories for BNF and BNFc implemented
Applying Formulary Status for Drug Therapeutic combination. (Adding, editing, and auditing included)

## Slide 14
Sprint 9 – Retrospective
  What Worked
    Frequent check-ins, and prompt code reviews
    High level design approval from Ian.
  What can be improved
    Stable Development and test environment.
      Two separate environments being created on Cloud (Dev and QA)
    Questions on functionalities to be asked earlier in the sprint.

## Slide 15
Risks & Impact
Non Stable Development and Test environment – The delay caused due to environmental issues can impact deliverables..
Mitigation
  Contingency
    Environment issues identified in previous sprint are to be resolved on priority.
    Multiple meetings if required to iron out open issues.
  Contingency
  Impact
    Budget and Schedule

## Slide 16
Risks & Impact contd.
Turnaround time for clarifications – Clarifications if not answered at the earliest could impact on the deliverables/ cause rework.
  Mitigation
    Rave to proactively share list of clarifications with RPS periodically.
    RPS to reply to clarifications with a one day turnaround time to minimize the impact on the deliverables and avoid rework.
  Contingency
    Rave to continue development making assumptions
  Impact
    Idle Time, Budget and Schedule

## Slide 17
Risks & Impact contd.
Not following coding best practices – Code not following best practices, leads to Refactoring of code. This causes rework and impacts deliverables.
Mitigation
    Peer review before checking-in code.
    Ensuring the issues identified in earlier review are not repeated.
  Contingency
  Impact
    Budget and Schedule

## Slide 18
Risks & Impact contd.
Delay in finalizing web design – The delay in not getting a sign-off early into the sprint can impact deliverables..
Mitigation
    Quick response from RPS on proposed changes by web design team
    Multiple meetings if required to iron out open issues.
    Discussion of design before working on a new module.
  Contingency
  Impact
    Budget and Schedule

## Slide 19
Questions?