## Plan for Sprint 7
|  | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon
|  | 5th | 6th | 7th | 8th | 11th | 12th | 13th | 14th | 15th | 18th | 19th | 20th | 21st | 22nd | 25th | 26 | 27 | 28 | 29 | 1
M | Rendering Home Page | Mon 27: done
| Hide paediatric formulary (or adult) | Mon 27: done
AA | Formulary Status (add, edit, display) | Mon 27: done
AJ | View earlier versions | Mon 27: 63 64
AJ | Sequence for notes | Mon 27: 57
M | Local Files and Local URLs | bar: Thu 14th to Mon 25th
M | User Authentication | bar: Tue 5th to Mon 25th
M | Search enhancements | bar: Fri 15th to Mon 25th
K | Changes to Audit Logs | bar: Mon 18th to Mon 25th
K | Export Formulary Report | Mon 29: 1064; Mon 1: 1024
| Including SMC and AWMSG | Mon 1: 56
| Display BNF content | Mon 29: 40
Roll over from Sprint 5 | bar: Tue 5th to Mon 25th
Plan for Migration
|  | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon
|  | 5th | 6th | 7th | 8th | 11th | 12th | 13th | 14th | 15th | 18th | 19th | 20th | 21st | 22nd | 25th
| Migration Activity | Wed 20th: QA Support
Parallel testing for Migration
Development | bar: Tue 5th
Testing | bar: Tue 5th
Holiday Offshore | bar: Tue 5th

## Test Plan
|  | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon
|  | 5th | 6th | 7th | 8th | 11th | 12th | 13th | 14th | 15th | 18th | 19th | 20th | 21st | 22nd | 25th | 26th | 27th | 28th | 29th | 1st
M | Rendering Home Page | bar: Tue 5th to Fri 8th; Tue 12th to Wed 13th; Fri 15th; Tue 19th; Thu 21st; Mon 25th; Wed 27th
Hide paediatric formulary (or adult) | bar: Fri 15th; Tue 19th; Thu 21st; Mon 25th; Wed 27th
AA | Formulary Status (add, edit, display) | bar: Tue 5th to Fri 8th; Tue 12th to Wed 13th; Fri 15th; Tue 19th; Thu 21st; Mon 25th; Wed 27th
AJ | View earlier versions | bar: Fri 15th; Tue 19th; Thu 21st; Mon 25th; Wed 27th
AJ | Sequence for notes | bar: Tue 5th to Fri 8th; Tue 12th to Wed 13th; Fri 15th; Tue 19th; Thu 21st; Mon 25th; Wed 27th
M | Local Files and Local URLs | bar: Fri 15th; Tue 19th; Thu 21st; Mon 25th; Wed 27th
M | User Authentication | bar: Tue 5th to Fri 8th; Tue 12th to Wed 13th; Fri 15th; Tue 19th; Thu 21st; Mon 25th; Wed 27th
M | Search enhancements | bar: Fri 15th; Tue 19th; Thu 21st; Mon 25th; Wed 27th
K | Changes to Audit Logs | bar: Tue 19th; Thu 21st; Mon 25th; Wed 27th
K | Export Formulary Report | bar: Tue 5th to Fri 8th; Tue 12th to Wed 13th; Fri 15th; Tue 19th; Thu 21st; Mon 25th; Wed 27th
Code Change for new Formulary Index for each formulary | bar: Tue 5th to Fri 8th; Tue 12th to Wed 13th; Fri 15th; Tue 19th; Thu 21st; Mon 25th; Wed 27th
Including SMC and AWMSG | bar: Fri 15th; Tue 19th; Thu 21st; Mon 25th; Wed 27th
Display BNF content | bar: Tue 5th to Fri 8th; Tue 12th to Wed 13th; Fri 15th; Tue 19th; Thu 21st; Mon 25th; Wed 27th
Roll over from Sprint 5 | bar: Tue 5th to Fri 8th; Tue 12th to Wed 13th; Fri 15th; Tue 19th; Thu 21st; Mon 25th; Wed 27th
Development | bar: Tue 5th
Testing | bar: Tue 5th
Holiday Offshore | bar: Tue 5th
Main Release | bar: Tue 5th

## Details of Delivery
| Main Release 1 | Main Release 2 | Main Release 3 | Interim Release | Main Release 4 | Main Release 5 | Main Release 6
| Mon 11/01 | Thu 14/01 | Monday 18/01 |  | Wed 20/01 | Fri 22/01 | Thu 28/01 | Remarks
Rendering Home Page |  |  |  |  | Y
Hide paediatric formulary (or adult) |  |  |  | Y
Formulary Status (add, edit, display) | [5 empty] | Y
View earlier versions |  |  |  |  | Y
Sequence for notes | [6 empty] | Y | Will be partly released in earlier intermittent releases
Local Files and Local URLs |  |  | Y
User Authentication | [6 empty] | Y
Search enhancements | [6 empty] | Y
Changes to Audit Logs | [5 empty] | Y
Export Formulary Report | [6 empty] | Y | Will be partly released in earlier intermittent releases
Including SMC and AWMSG | [5 empty] | Y
Display BNF content |  |  |  |  | Y
Code Change for new Formulary Index for each formulary | [5 empty] | Y

## Sheet4
|  | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon
|  | 5th | 6th | 7th | 8th | 11th | 12th | 13th | 14th | 15th | 18th | 19th | 20th | 21st | 22nd | 25th
M | Rendering Home Page | bar: Tue 5th to Tue 19th
AA | Formulary Status (add, edit, display)
AJ | View earlier versions | bar: Thu 14th to Mon 25th
AJ | Sequence for notes
M | Local Files and Local URLs | bar: Thu 14th to Mon 25th
M | User Authentication
M | Search enhancements | bar: Fri 15th to Mon 25th
K | Export Formulary Report
Including SMC and AWMSG | bar: Thu 14th to Mon 25th
Display BNF content
Roll over from Sprint 5
Plan for Migration
|  | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon
|  | 5th | 6th | 7th | 8th | 11th | 12th | 13th | 14th | 15th | 18th | 19th | 20th | 21st | 22nd | 25th
| Migration Activity | Wed 20th: QA Support
Parallel testing for Migration
Development | bar: Tue 5th
Testing | bar: Tue 5th
Holiday Offshore | bar: Tue 5th

## Sheet5
Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon
5th | 6th | 7th | 8th | 11th | 12th | 13th | 14th | 15th | 18th | 19th | 20th | 21st | 22nd | 25th | 26th | 27th | 28th | 29th | 1st
M
K
At
Aa
Aj
Bh
Po
Sn
| 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 3 | 3 | 3 | 3 | 3 | 127
Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon
5th | 6th | 7th | 8th | 11th | 12th | 13th | 14th | 15th | 18th | 19th | 20th | 21st | 22nd | 25th | 26th | 27th | 28th | 29th | 1st
M
K
At
Aa
Aj
Bh
Po
Sn
| 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 4 | 4 | 4 | 4 |  | 126
Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon
5th | 6th | 7th | 8th | 11th | 12th | 13th | 14th | 15th | 18th | 19th | 20th | 21st | 22nd | 25th | 26th | 27th | 28th | 29th | 1st
M
K
At
Aa
Aj
Bh
Po
Sn
| 8 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4 |  | 115
| 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 3 | 3 | 3 | 3 | 3 |  | 127