## Slide 1
RPS – FORMULARY COMPLETE
Sprint 2 Planning Meeting

## Slide 2
Agenda
Sprint 1 – Planned Deliverables’ Status
Sprint 1 – Retrospective
Sprint 2 – Backlog
Sprint 2 – Calendar
Change Requests
Risks & Impact
Questions?

## Slide 3
Sprint 1 – Planned Deliverables’ Status
User Story | Summary | Remarks | Status
FC 98 FC 100 | Sprint 1 base case: View BNF and BNFC records | Requires extensive regression testing | Development complete. Testing in Progress
FC 16 | Navigate to record through expandable tree view of contents |  | Completed
FC 17 | Navigate to records through breadcrumb trail |  | Completed
FC 24 | Alert + link to summary when NICE Technology appraisal applies to drug monograph |  | Completed
FC 26 | NICE Technology appraisal summary will include link to external NICE web page |  | Completed
FC 18 | On a BNF/BNFC record page any locally added information should be prominent |  | Pending
FC 75 | Boilerplate data |  | Completed

## Slide 4
Cont..
Sprint 1 – Planned Deliverables’ Status
User Story | Summary | Remarks | Status
FC 42 | Local record creation |  | Completed
FC 44 | Local record renaming |  | Completed
FC 45 | Local record renaming |  | Completed
FC 99, FC 20 | • Interactions data for a drug from a list in tree view of contents | Data not appearing in Elastic Search database | Pending
FC 21, FC 22 | • Record pages to include “Related information” links panel • “Related information” links to include corresponding records for the same drug in the other formulary | Development over, unit testing in progress | Pending
FC 10 | Default choice of three colour-coded formulary statuses to be editable and expandable to ten |  | Pending

## Slide 5
Sprint 1 – Retrospective
  What Worked
    Prompt Response from the RPS Team for the queries raised by Rave.
    Offshore team picking up speed, especially in latter half of sprint.
    Well conducted (concise and effective) Scrum Meetings.
    Coordination between members of Rave team and James.
  What can be improved
    Web interface should have been frozen very early into the sprint.
      Demo session scheduled tomorrow, to freeze the web UI design for all stories for sprint 2 and some functionality for future sprints
      Going forward the mock up will be frozen before the sprint commences.
      The code has to be made more “Scala like”.
        Code review has to be conducted regularly and inputs from Ian, James have to be incorporated immediately.

## Slide 6
Sprint 2 – Backlog
    The offshore team proposes the following to be completed in Sprint 2
      Edit content: individual record notes
      Find drug information. (complete)
      Edit content Formulatory Status (James)
      Edit content: nodes (complete)

## Slide 7
Sprint 2 Calendar

## Slide 8
Definition of Done
Definition of Done will be the System Test Cases as approved by RPS

## Slide 9
Change Requests
Not Applicable

## Slide 10
Risks & Impact
Sprint timelines are short – it will tough to complete development and testing of all the planned deliverable items.
  Mitigation
    Rave to provide proactive update to the IET if any deliverable needs to be deferred to next releases.
    Rave to try to test the deliverables in maximum browsers and devices.
  Contingency
    Rave to deliver the deferred items and pending browser-devices testing in upcoming sprint.
  Impact
    Idle Time, Budget and Schedule

## Slide 11
Risks & Impact
Turnaround time for clarifications – Clarifications if not answered at the earliest could impact on the deliverables/ cause rework.
  Mitigation
    Rave to proactively share list of clarifications with RPS periodically.
    RPS to reply to clarifications with a one day turnaround time to minimize the impact on the deliverables and avoid rework.
  Contingency
    Rave to continue development making assumptions
  Impact
    Idle Time, Budget and Schedule

## Slide 12
Questions?