## Slide 1
RPS – FORMULARY COMPLETE
Sprint 2 Review

## Slide 2
Agenda
Sprint 2 – Planned Deliverables’ Status
Sprint 2 – Retrospective
Sprint 3 – Stabilization Sprint
Sprint 3 – Calendar
Change Requests
Risks & Impact
Questions?

## Slide 3
Sprint 2 – Planned Deliverables’ Status
User Story | Summary | Status | Remark
FC 60 | • Adding local content | Development complete. Testing in Progress | Requires extensive regression testing
FC 54, FC 58 | • amend the text of local content • submit my created/edited record for approval • have the option of publishing my created/edited record immediately |  | System Testing In Progress
FC 40 | • submit an entire note deletion instruction for approval |  | System Testing In Progress
FC 47 | • Reusable content creation |  | Requires extensive regression testing

## Slide 4
Sprint 2 – Planned Deliverables’ Status
User Story | Summary | Status | Remark
FC 48, FC 49 | • Reusable content anchoring/location • Reusable content anchoring: disambiguation of location context | Completed | Requires extensive regression testing
FC 51, 52 | • Reusable content editing • Reusable content formatting | Pendng | 
FC 12 and FC 15 | • Search for drug • Search for Medicinal Product/preparations • Search for treatment summaries • Grouping of Search Results | Completed | 
FC 42 | • Local record creation | Completed | 

## Slide 5
Sprint 1 – Planned Deliverables’ Status
User Story | Summary | Status | Remark
FC 44 | • Local record renaming | Completed | 
FC 45 | • Local record deletion | Completed | 
FC 99, FC 20 | • Interactions data for a drug from a list in tree view of contents | Pending | Data not appearing in Elastic Search database.
FC 21, FC 22 | • Record pages to include “Related information” links panel and open drug |  | Development over, unit testing in progress
FC 10 | • Three colour-coded formulary statuses to be editable and expandable to ten | Pending | 

## Slide 6
Sprint 1 – Retrospective
  What Worked
    Prompt Response from the RPS Team for the queries raised by Rave.
    Well conducted (concise and effective) Scrum Meetings.
    Coordination between members of Rave team and James.
  What can be improved
    Web interface should have been frozen very early into the sprint.
      Stabilization Sprint to be used for freezing the web front end for future sprints

## Slide 7
Sprint 2 – Stabilization Sprint
    The offshore team proposes the following for the Stabilization Sprint
      Stabilize all the delivered functionality. Get a sign off .
      Complete all pending work from Sprint 1 and Sprint 2
      Close all open defects/issues.
      Freeze on the new Elastic Search Database for holding customer data.
      Finalize the web front end design for future sprints.
      Complete the migration strategy, and plan on initiating the migration activity

## Slide 8
Sprint 3 Calendar

## Slide 9
Definition of Done
Definition of Done will be the System Test Cases as approved by RPS

## Slide 10
Change Requests
Not Applicable

## Slide 11
Risks & Impact
Turnaround time for clarifications – Clarifications if not answered at the earliest could impact on the deliverables/ cause rework.
  Mitigation
    Rave to proactively share list of clarifications with RPS periodically.
    RPS to reply to clarifications with a one day turnaround time to minimize the impact on the deliverables and avoid rework.
  Contingency
    Rave to continue development making assumptions
  Impact
    Idle Time, Budget and Schedule

## Slide 12
Questions?