## Slide 1
RPS – FORMULARY COMPLETE
Sprint 4 Planning

## Slide 2
Agenda
Sprint 3 Deliverables’ Status
Sprint 3 Retrospective
Sprint 3 metrics
Project Status
Sprint 4 Plan
Sprint 4 Implementation Plan A
Sprint 4 Implementation Plan B (Contingency)
Change Requests
Risks & Impact
Questions?

## Slide 3
Sprint 3 – Deliverables’ Status
User Story | Summary | Status | Remark
FC 212, 213 and 214 | • Refactoring for Pharma Press - Drug Services • Refactoring for Pharma Press - Search Services • Refactoring for Pharma Press - Admin Services | Completed Completed Completed | All changes have been done and are awaiting review
FC 215, 216 and 217 | • Refactoring - Search Module • Refactoring - Local Records Listing • Refactoring - Local Records Creation | Incomplete 50% Completed Completed | “Futures” implementation. All changes are awaiting review
FC 218 | • Monograph - Template Implementation | Incomplete | Header and footer template segregation is complete. James to render BNF content in templates
FC 219 | • Data Model | Completed | Under Review

## Slide 4
Sprint 3 – Deliverables’ Status
User Story | Summary | Status | Remark
FC 220 | • Logger Implementation | Incomplete 60% | Completed for 2 services. Will be delivered in next 2 days
FC 221 | • Exception Handling Server Side Client Side | Incomplete 50% | Server side exception handling has been completed for Admin.
FC 223 | • Object Mapper Changes | Incomplete 30% | This is pending implementation at web App
FC 222 | • Scala Unit Tests | Incomplete 50% | Completed for Search. Pending for Admin and Drug (Services)
FC 10 | UI Changes for : • Monograph • Notes and Records Page • Generation of TOC • Search Page | Pending | The previously delivered functionality is to be restored, and look and feel updated to the latest.

## Slide 5
Sprint 3 – Deliverables’ Status (Web design)
User Story | Summary | Status | Remark
FC230 | • Monograph Changes | Complete | Awaiting Feedback The web design is in progress. Awaiting Feedback
 | • Export formulary content | Complete | 
 | • Managing Work queue | Complete | 
 | • Edit Local content (Records) • Edit Content Notes | Complete | 
 | • Edit content: formulary status | incomplete | 
 | • View changes across BNF versions | Complete | 

## Slide 6
Sprint 3 – Goals and status
Goal for the Stabilization Sprint | Status | Remarks
All common dependencies factored out, and everyone on the same code base | Completed | 
All projects building automatically on check in to Github | In Progress | This activity is with James
Daily automatic deployment of projects to Azure | Completed | 
Up to date ElasticSearch on Azure | In Progress | Pending for Admin Module
Web-app re-factored to controller, Service, with dependency injection | In Progress FC 212- 218 | Nearing completion. Checked in code is under review
Unit Tests for controllers and services | In Progress FC-222 | Pending Admin and Drug Services
View templates with common codes extracted into separate templates | Completed | 
Drug monograph template re-factored with separate templates for each pot | In Progress | 
Using Json Format (removing Object Mapper | In Progress | Nearing completion.

## Slide 7
Sprint 3 – Retrospective
  What Worked
    Visit by Ian, Harvey and James.
    Frequent check-ins, and prompt code reviews.
    Refactoring Activities.
  What can be improved
  Deliverables.
    Peer review before checking-in code.
    Ensuring the issues identified in earlier review are not repeated.
    Discussion of design before working on a new module.
    Web UI design to be finalized as early as possible in the sprint.
    Logging time in JIRA
    Questions on functionalities to be asked earlier in the sprint.

## Slide 8
Sprint 3 – Metrics
  Story points planned - 56 SP
  Story points delivered 30 SP

## Slide 9
Overall Project Status
Project Deliverables | Plan of Delivery | Revised Plan of Delivery | Remarks
User Accounts | Sprint 1 | Sprint 5 | Integration with SAMS is still pending.
Search Module | Sprint 2 | Sprint 4 | Basic Search module had been delivered in sprint2. Re-factored Search module is being tested. Monograph page is not completed so far
Edit the content: formulary status | Sprint 2 | Sprint 5 | Existing code to be changed to point to ES.
Edit the local content | Sprint 2 | Sprint 4 | The add/update/delete for local content and notes had been delivered earlier. Post code refactoring, functionality will be restored within first week of sprint 4
Edit Notes | Sprint 2 | Sprint 4 | 

## Slide 10
Overall Project Status contd.
Project Deliverables | Plan of Delivery | Revised Plan of Delivery | Remarks
Monitor content changes: approval /workflow | Sprint 4 | Sprint 4 | No Change in overall project Plan
Monitor content changes: audit | Sprint 4 | Sprint 5 | These reports are still under discussion
Export formulary content | Sprint 4 | Sprint 4 | No Change in overall project Plan
Admin Module | Sprint 4 | Sprint 5 | Web design is to be finalized
Drug Comparison | Sprint 5 |  | De-scoped (Comparison across drugs still in scope)
Annotation Search | Sprint 5 |  | De-scoped
View Changes across BNF versions | Sprint 5 | Sprint 4 | Reduced scope
Migration Activity | Sprint 3 onwards | Sprint 5 | Ian to visit in November and bring this to closure

## Slide 11
Sprint 4 Plan
Tasks | Details | Remarks
Continue work for Refactoring/ code quality/ unit test | Scala tests are to be implemented for Services “Futures’ implementation Removal of Object Mapper | The aim is to finish of this work latest by 30th October.
Restoring earlier delivered functionality | Search functionality, Table of Content , and admin module (records and notes) All updated with latest look and feel changes. | Need sign off on web design as soon as possible.
Removing all session state |  | 
Rendering BNF content correctly. | Monograph Changes | James is looking at this.
Creating Access Management micro-service and linking site to it | This service would supply mock authentication to the FC till a decision is taken on SAMs | 

## Slide 12
Sprint 4 Plan
Tasks | Details | Remarks
Managing Work queue | New Functionality. Monitor content changes: approval/workflow . | The web design is under review Need to be signed off before 30th Oct.
View Changes across BNF versions | New Functionality. Screen to provide user an option to view changes across BNF versions | The web design is under review Need to be signed off before 30th Oct.
Export Formulary Content | New Functionality. Report to view and export details of formulary content, based on different parameters. | The web design is under review Need to be signed off before 30th Oct.

## Slide 13
Sprint 4 Plan - A

## Slide 14
Sprint 4 Plan – B (contingency)
Plan B does not include the export formulary content.
This plan will come into play if there is any deviation in planned deliverables for week ending 30th October.

## Slide 15
Definition of Done
Definition of Done will be the System Test Cases as approved by RPS

## Slide 16
Change Requests
Not Applicable

## Slide 17
Risks & Impact
Turnaround time for clarifications – Clarifications if not answered at the earliest could impact on the deliverables/ cause rework.
  Mitigation
    Rave to proactively share list of clarifications with RPS periodically.
    RPS to reply to clarifications with a one day turnaround time to minimize the impact on the deliverables and avoid rework.
  Contingency
    Rave to continue development making assumptions
  Impact
    Idle Time, Budget and Schedule

## Slide 18
Questions?