## Read Me
Code review Guideline
Responsibility
1 | Code reviews shall be performed by peers, i.e. by other developers on the project who have a good knowledge of product & language. | Reviewer
2 | Correct Sprint No. should be updated at the start of the review by reviewer in Sub Project section. | Reviewer
3 | In the Summary box, enter the brief description of user story which is under review. | Reviewer
4 | In the Description box, describe the issue in detail. It can contain the reference details or steps to reproduce that issue. | Reviewer
5 | In the Reported By box, mention the Name of the person who reported the issue, reviewer's name. | Reviewer
7 | In the Coded By box, Select the name of the person who was responsible for coding under the module in which issue occurs | Reviewer
6 | Reported date - Date on which review comments are given. | Reviewer
8 | Responsible Person - Select the person who will be responsible for addressing review comments | Reviewer
6 | Multiple comments can be marked for single module. Also, if there are no comments then Description should be updated with No review comments. | Reviewer
7 | Once the code review is completed, comments will be updated in Description column by reviewer & will be shared with Code Owner for further actions. | Reviewer
8 | Code Owner should go through the review comments & to check the applicability of comments shared | Owner of code
10 | If the comments are rejected then comments for rejection should be updated in Code Owner's comments section. Also if further information is required then comments should be updated for Code Owner's comments accordingly. | Owner of code
13 | If code owner has any comments to share with reviewer, comments should be updated in Owner's comments column | Owner of code
14 | Once code changes are implemented then Status column should be updated with Implemented , if code comments are still open or undergoing chnages then Status should be marked as Open. | Owner of code

## RPS Sprint-1
|  |  | Project Name : | RPS |  |  |  |  | `
|  |  | Sprint : | 1
Sr. No | JIRA Ref | File Name | Change Description | Coded By | Reviewer's Comments | Reviewed By | Reviewed Date | Code Owners Comments | Responsible Person | Status | Closure Date
1 |  | formulary-complete- webapp->DrugController.scala | changes Made according to the instruction | Jitendra | Replace If statements with scala match case | shital madake | 2015-09-08 | No Comments | Jitendra | Completed | 2015-09-14
[5 empty] | Return keyword not required |  |  | No Comments | Jitendra | Open
[5 empty] | println statemts are not required |  |  | No Comments | Jitendra | Done | 2015-09-15
2 |  | monograph.scala.html | changes Made according to the instruction | Jitendra | 1] Content Structure | shital madake | 2015-09-08 | No Comments | Jitendra | Completed | 2015-09-18
[5 empty] | 2] ordering or the contents |  |  | No Comments |  | Completed | 2015-09-18
3 |  | DrugInfoService | changes Made according to the instruction |  | 3] return statement not required |  |  | No Comments |  | Open | 2015-09-18
4 |  | formulary-complete-webapp-> HierarchyController.scala | changed | Mohini | It could be written more clearly and shortly getObjectMapper | shital madake | 2015-09-08 | No Comments | Mohini | Completed | 2015-09-21
5 |  | pharmpress-drug-services->DrugSearchController.scala | changed | Mohini | It could be written more clearly and shortly getObjectMapper | shital madake | 2015-09-14 | No Comments | Mohini | Completed | 2015-09-23
6 |  | pharmapress-services-> HierarchyController.scala | changed | Mohini | It could be written more clearly and shortly getObjectMapper | shital madake | 2015-09-14 | No Comments | Mohini | Completed | 2015-09-23
7 |  | HierarchyInfoDao.scala | chnaged | Mohini | It could be written more clearly and shortly getObjectMapper | shital madake | 2015-09-15 | No Comments | Mohini | Completed | 2015-09-23
Note on C5: Santosh Tikekar: File Name which is being review
Note on D5: User story under review
Note on F5: Issue in detail
Note on G5: Reviewer Name
Note on J5: Person responsible for addressing review comments
Note on K5: prachi.gaonkar: Status of the comment
Note on L5: prachi.gaonkar: Date on which comments implemented in Code, to be filled by Owner of the code

## RPS Sprint-2
|  |  | Project Name : | RPS |  |  |  |  | `
|  |  | Sprint : | 2
Sr. No | JIRA Ref | File Name | Change Description | Coded By | Reviewer's Comments | Reviewed By | Reviewed Date | Code Owners Comments | Responsible Person | Status | Closure Date
1 |  | formulary-complete-develop\pharmpress-services\app\com\pharmpress |  | Jitendra | Change Name of woundmanagement | shital & jitendra | 2015-09-28 | No Comments | Jitendra | Peniding
|  |  | Changes has been made according to the instruction | Jitendra | [5 empty] | Completed | 2015-10-01
2 |  | formulary-complete-develop\pharmpress-services\app\com\pharmpress | Changes has been made according to the instruction | Jitendra | Merge Two folgers of woundmanagement and check the spelling of it | shital & jitendra | 2015-09-30 | No Comments | Jitendra | Completed | 2015-10-01
3 |  | URL:- http://rav-dsk-313:9000/Admin/AddUpdateLocalContent | Changes has been made according to the instruction | UI | showing -> sign on top left corner | shital | 2015-10-03 | No Comments | UI | Completed
4 |  | com.pharmpress.search.dao. SearchInfoDao |  | Mohini | Need to import scala.collection.mutable on top for Map | Shital | 2015-10-03 | No Comments | Mohini | Open
5 |  | formulary-complete-webapp routes | done | abin | 1] change name /borderline to borderlineSubstance
2] node needs to be records
3] rename Admin to admin+F2
[5 empty] | 4] rename save to saveSnippet | shital | 2015-10-06 | No Comments | Abin | Closed | 2015-10-08
6
Note on C5: Santosh Tikekar: File Name which is being review
Note on D5: User story under review
Note on F5: Issue in detail
Note on G5: Reviewer Name
Note on J5: Person responsible for addressing review comments
Note on K5: prachi.gaonkar: Status of the comment
Note on L5: prachi.gaonkar: Date on which comments implemented in Code, to be filled by Owner of the code

## RPS Sprint-3
|  |  | Project Name : | RPS |  |  |  |  | `
|  |  | Sprint : | 3
Sr. No | JIRA Ref | File Name | Change Description | Coded By | Reviewer's Comments | Reviewed By | Reviewed Date | Code Owners Comments | Responsible Person | Status | Closure Date
Note on C5: Santosh Tikekar: File Name which is being review
Note on D5: User story under review
Note on F5: Issue in detail
Note on G5: Reviewer Name
Note on J5: Person responsible for addressing review comments
Note on K5: prachi.gaonkar: Status of the comment
Note on L5: prachi.gaonkar: Date on which comments implemented in Code, to be filled by Owner of the code

## RPS Sprint-4
|  |  | Project Name : | RPS |  |  |  |  | `
|  |  | Sprint : | 4
Sr. No | JIRA Ref | File Name | Change Description | Coded By | Reviewer's Comments | Reviewed By | Reviewed Date | Code Owners Comments | Responsible Person | Status | Closure Date
Note on C5: Santosh Tikekar: File Name which is being review
Note on D5: User story under review
Note on F5: Issue in detail
Note on G5: Reviewer Name
Note on J5: Person responsible for addressing review comments
Note on K5: prachi.gaonkar: Status of the comment
Note on L5: prachi.gaonkar: Date on which comments implemented in Code, to be filled by Owner of the code

## RPS Sprint-5
[6 empty] | Project Name : | RPS
[6 empty] | Sprint : | 5
Sr. No | JIRA Ref | File Name | Change Description | Coded By | Reviewer's Comments | Reviewed By | Reviewed Date | Code Owners Comments | Responsible Person | Status | Closure Date
Note on C5: Santosh Tikekar: File Name which is being review
Note on D5: User story under review
Note on F5: Issue in detail
Note on G5: Reviewer Name
Note on J5: Person responsible for addressing review comments
Note on K5: prachi.gaonkar: Status of the comment
Note on L5: prachi.gaonkar: Date on which comments implemented in Code, to be filled by Owner of the code

## RPS Sprint-6
[6 empty] | Project Name : | RPS
[6 empty] | Sprint : | 6
Sr. No | JIRA Ref | File Name | Change Description | Coded By | Reviewer's Comments | Reviewed By | Reviewed Date | Code Owners Comments | Responsible Person | Status | Closure Date
Note on C4: Santosh Tikekar: File Name which is being review
Note on D4: User story under review
Note on F4: Issue in detail
Note on G4: Reviewer Name
Note on J4: Person responsible for addressing review comments
Note on K4: prachi.gaonkar: Status of the comment
Note on L4: prachi.gaonkar: Date on which comments implemented in Code, to be filled by Owner of the code

## Sheet1
14829 | 14829 | TB-152 | 2015-08-25 18:26 | Update url flag set to false
2 | 14828 | Amit Desai | TB-152 | 2015-08-25 18:18 | Issue with video play from event landing page
3 | 14822 | Amit Desai | TB-152 | 2015-08-24 19:01 | TB-152 : QA issues
4 | 14821 | Madhura Mungekar | TB-155 | 2015-08-24 17:33 | date format change
5 | 14817 | Babaso Mahadik | TB-145 | 2015-08-21 18:16 | Changes made for TB-145 for multiple file creation
6 | 14814 | Madhura Mungekar | TB-155 | 2015-08-21 13:15 | TB-155 video date format defect
7 | 14813 | Amit Desai | TB-152 | 2015-08-21 12:49 | TB-152 log in check
8 | 14810 | Amit Desai | TB-152 | 2015-08-20 12:10 | script and css version changes sprint-5.1
9 | 14809 | Amit Desai | TB-152 | 2015-08-20 12:01 | kaltura changes
10 | 14808 | Madhura Mungekar | TB-155 | 2015-08-20 11:23 | Changes for TB-155 video date format changed in XML
11 | 14807 | Amit Desai | TB-152 | 2015-08-19 21:27 | TB-152 changes
12 | 14806 | Ashwini Gawade | TB-172 | 2015-08-19 19:29 | chnages for perticular account selection while generating report
13 | 14804 | Babaso Mahadik | TB-161 | 2015-08-19 17:27 | TB-161
14 | 14803 | Babaso Mahadik | TB-161 | 2015-08-19 17:26 | TB-161
15 | 14802