## Doc Info
Document |  | : | RPS Formulary Complete Product Replacement - Agile checklist
Issue |  | : | 1
Filename |  | : | RPS Formulary Complete Product Replacement - Agile checklist.xlsx
Author |  | : | Sandarbh Sharma
Date |  | : | 2015-08-10
Revision History
Version No | Author |  | Approver | Release Date | Description of changes
1 | Sandarbh Sharma |  |  | 2014-09-21 | Created

## Agile
Phase | Process requirement | Required | Artefacts | References/Exceptions
Requirements | Capturing user requirements with NFRs | Mandatory | User stories document | JIRA wiil be used for monitoring & tracking of the requirements & stories. | User stories document, Sprint backlog document
Release planning | Release plan to help forecast the project end date | Mandatory | Release Planning document/presentation | Release document is created for high level plan. The targetted dates i.e Sprint calendar is part of the Sprint planning backlog. | Sprint Planning document, MOM for planning meeting, Presentation
Estimation | Methodology & mode of capture | Mandatory | Poker Planning | Esimation is done with reference to story points. | PSR, Mail with discussion points and action items
Sprint planning | Plan for each individual sprint consisting of - resources - scope - timelines | Mandatory | Sprint backlog | Backlog from JIRA would be used in sprint planning meeting. | Design document, Architechture
DOD | This needs to be defined for each sprint in order to achieve targetted completion | Mandatory |  | The clearance of system test is Definition of Done. A Backlog item must be marked as done after the system Testers complete the testing as per the Acceptance criteria that is mentioned for each story in the JIRA. | change request document, Impact analysis document, Revised sprint plan
Requirements Traceability | From requirements to design,test case | Mandatory | Test Case document | These are captured in JIRA | Unit test case document
Project Status report | This could include - Daily standups - Formal status report to customers | Mandatory |  | Daily Standups meeting with Client to update status. Status Dashboard is used for sharing the status with the client. | SIT test cases and results
Unit testing | Process | Mandatory | TDD (Automated Test cases) | This is checked in as part of code | SIT test cases review document, Issue in whizible, Review mail
Review | Includes all stages of review: - Requirements - Design - Code - System Test Case | Mandatory | Excel / word | Jira is being used for comments sharing on requirements. Code reviews are tracked through excel | Release notes, Installation guide
System Testing |  | Mandatory | Tool (specify alongside) | JIRA is used for tracking. | User manual, Project guide, Evidence for User training
Release |  | Mandatory | Release notes | Documemnts to be kept in GItHub
Sprint review |  | Mandatory | Demo in defined meetings | Frequent demos are shown to the client.
Sprint Retrospective | Documents activities that we need to start doing, continue doing or stop doing | Mandatory | LLR captured word/excel | This is a part of the Sprint planning meeting.
Product documentation |  | Optional |  | These are captured in JIRA
[7 empty] | Baselining Requirements | Requirements Clarity | Sprint planning | Project Status report (periodic) | Design | Change Management | Unit testing | UT review | Code review | System Testing | SIT test case review | Release | User help
[6 empty] | Mandatory | User stories document | Clarification log | Sprint Planning document | PSR document | Design document | Change request document | Unit test case document | UTC review mail | Code review checklist | SIT test cases and results | SIT test cases review document | Release notes | User manual
[6 empty] | Optional | Sprint backlog document | Mails | MOM for planning meeting | Mail with discussion points and action items | Technical Architechture | Impact analysis document | TDD (Automated Test cases) | Issue in whizible | Issue in whizible |  | Issue in whizible | Installation guide | Project guide
[9 empty] | Sprint planning Presentation |  |  | Revised sprint plan |  |  |  |  | Review mail |  | Evidence for User training

## Values
Requirements | Release planning | Estimation | Sprint planning | DOD | Requirement Tracebility | Project Status report (periodic) | Unit testing | Review | System Testing | Release | Sprint review | Sprint Retrospective | Product documentation
User stories document | Release Planning document/presentation | Poker Planning | Sprint Planning document/presentation |  | Requirements Traceability Matrix | PSR document | Unit test case document | Excel / word | SIT test cases and results | Release notes | Demo in defined meetings | LLR captured word/excel | User manual
Product / Sprint backlog document |  | WBS | Sprint backlog |  | Test Case document | Mail with discussion points and action items | TDD (Automated Test cases) | Whizible | Tool (specify alongside) | Installation guide |  |  | Product guide
[6 empty] | Action item log |  | Others (please specify)