## Plan for Sprint
Reference | Summary of user Story /Work | Owned by | Development Start Date | Development End Date | Deviation (if Any) | Test Start Date | Test End Date | Deviation (if Any) | Status RAG | Remarks
Data structure (including SAAS considerations)
| Data Structure creation in ES | Sandarbh and Abin | 2015-09-21 | 2015-09-22
Edit the content: individual record notes (Annotations)
E1 | add a note to a record | Aarti, Abin | 2015-09-18 | 2015-09-23
E2 | amend the text of a note in a record | Aarti, Abin | 2015-09-18 | 2015-09-23
E3 | refer to the previous versions of a record when I’m editing a note | Aarti, Abin | 2015-09-24 | 2015-09-25
E4 | apply simple formatting to the text of a note in a record – bold/italic/underlined; font size; font color; highlighting; list indentation; range left/right/centre and be able to insert web links | Aarti | 2015-09-18 | 2015-09-23
E5 | see how a record will look when the edits are published | Aarti | 2015-09-24 | 2015-09-25
E6 | submit my created/edited note for approval | Aarti, Abin | 2015-09-18 | 2015-09-23
E7 | have the option of publishing my created/edited note immediately if I don’t want to seek approval | Aarti, Abin | 2015-09-28 | 2015-10-01
E8 | submit an entire note deletion instruction for approval | Aarti, Abin | 2015-09-18 | 2015-09-23
E9 | have the option of deleting a note immediately if I don’t want to seek approval | Aarti, Abin | 2015-09-18 | 2015-09-23
Edit the content: nodes
E11 | append a placeholder (blank) record to a BNF/BNFC chapter or section,* or insert one in the local Documents | Aarti, Abin | 2015-09-28 | 2015-09-30
E13 | rename my own or colleagues' records | Aarti, Abin | 2015-09-28 | 2015-09-30
E14 | delete my own or colleagues' records | Aarti, Abin | 2015-09-28 | 2015-09-30
| submit my created/edited/deleted nodes for approval | Aarti, Abin | 2015-09-28 | 2015-09-30
Search Module
FC 12 and FC 15 | Search for drug | Mohini | 2015-09-21 | 2015-09-24
| Search for Medicinal Product/preparations | Mohini | 2015-09-21 | 2015-09-24
| Search for drug class | Mohini | 2015-09-28 | 2015-09-30
| Search for treatment summaries | Mohini | 2015-09-28 | 2015-09-30
| Grouping of Search results | Mohini | 2015-10-01 | 2015-10-05
Changes to TOC
| Implement Changes to TOC | Ajay, Jitendra | 2015-09-21 | 2015-09-23
Reusable Snippets (excluding targets)
FC-47 | Reusable content creation | Ajay, Abin | 2015-09-24 | 2015-09-28
FC-51 | Reusable content editing | Ajay, Abin | 2015-09-29 | 2015-10-01
FC-52 | Reusable content formatting | Ajay, Abin | 2015-09-29 | 2015-10-01
Rollover from Sprint 1
FC-98 | View BNF records | Jitendra | 2015-09-18 | 2015-09-21
FC-100 | View BNFC Records. | Jitendra | 2015-09-18 | 2015-09-21
FC-20 | Check BNF/BNFC drug against interactions database | Jitendra | 2015-09-18 | 2015-09-21
FC-99 | Find interactions data for a drug from a list in tree view of contents | Jitendra | 2015-09-18 | 2015-09-21
FC-21 | Record pages to include “Related information” links panel | Jitendra | 2015-09-22 | 2015-09-23
FC-22 | “Related information” links to include corresponding records for the same drug in the other formulary | Jitendra | 2015-09-22 | 2015-09-23
FC-18 | On a BNF/BNFC record page any locally added information should be prominent | Jitendra | 2015-09-22 | 2015-09-23
| Defect Closure (Sprint 1) | Shital and Web team | 2015-09-18 | 2015-09-21
| Automated unit testing completion for sprint 1 | Jitendra/ Abin/Shital | 2015-09-21 | 2015-09-29
| Interim release dates | Every alternate day starting 22 september
Note on F3: Sandarbh Sharma: Ian on leave from Wednesday

## Plan for contingency
Reference | Summary of user Story /Work | Owned by | Development Start Date | Development End Date | Deviation (if Any) | Test Start Date | Test End Date | Deviation (if Any) | Status RAG | Remarks
Data structure (including SAAS considerations)
| Data Structure creation in ES | Sandarbh and Abin | 2015-09-21 | 2015-09-22
Edit the content: individual record notes (Annotations)
E1 | add a note to a record | Aarti, Abin | 2015-09-18 | 2015-09-23
E2 | amend the text of a note in a record | Aarti, Abin | 2015-09-18 | 2015-09-23
E3 | refer to the previous versions of a record when I’m editing a note | Aarti, Abin | 2015-09-24 | 2015-09-25
E4 | apply simple formatting to the text of a note in a record – bold/italic/underlined; font size; font color; highlighting; list indentation; range left/right/centre and be able to insert web links | Aarti | 2015-09-18 | 2015-09-23
E5 | see how a record will look when the edits are published | Aarti | 2015-09-24 | 2015-09-25
E6 | submit my created/edited note for approval | Aarti, Abin | 2015-09-18 | 2015-09-23
E7 | have the option of publishing my created/edited note immediately if I don’t want to seek approval | Aarti, Abin | 2015-09-28 | 2015-10-01
E8 | submit an entire note deletion instruction for approval | Aarti, Abin | 2015-09-18 | 2015-09-23
E9 | have the option of deleting a note immediately if I don’t want to seek approval | Aarti, Abin | 2015-09-18 | 2015-09-23
Edit the content: nodes
E11 | append a placeholder (blank) record to a BNF/BNFC chapter or section,* or insert one in the local Documents | Aarti, Abin | 2015-09-28 | 2015-09-30
E13 | rename my own or colleagues' records | Aarti, Abin | 2015-09-28 | 2015-09-30
E14 | delete my own or colleagues' records | Aarti, Abin | 2015-09-28 | 2015-09-30
| submit my created/edited/deleted nodes for approval | Aarti, Abin | 2015-09-28 | 2015-09-30
Search Module
FC 12 and FC 15 | Search for drug | Mohini | 2015-09-21 | 2015-09-24
| Search for Medicinal Product/preparations | Mohini | 2015-09-21 | 2015-09-24
| Search for drug class | Mohini | 2015-09-28 | 2015-09-30
| Search for treatment summaries | Mohini | 2015-09-28 | 2015-09-30
| Grouping of Search results | Mohini | 2015-10-01 | 2015-10-05
Changes to TOC
| Implement Changes to TOC | Ajay, Jitendra | 2015-09-21 | 2015-09-23
Reusable Snippets (excluding targets)
FC-47 | Reusable content creation | Ajay, Abin | 2015-09-24 | 2015-09-28
FC-51 | Reusable content editing | Ajay, Abin | 2015-09-29 | 2015-10-01
FC-52 | Reusable content formatting | Ajay, Abin | 2015-09-29 | 2015-10-02
Rollover from Sprint 1
FC-98 | View BNF records | Jitendra | 2015-09-18 | 2015-09-21
FC-100 | View BNFC Records. | Jitendra | 2015-09-18 | 2015-09-21
FC-20 | Check BNF/BNFC drug against interactions database | Jitendra | 2015-09-18 | 2015-09-21
FC-99 | Find interactions data for a drug from a list in tree view of contents | Jitendra | 2015-09-18 | 2015-09-21
FC-21 | Record pages to include “Related information” links panel | Jitendra | 2015-09-22 | 2015-09-23
FC-22 | “Related information” links to include corresponding records for the same drug in the other formulary | Jitendra | 2015-09-22 | 2015-09-23
FC-18 | On a BNF/BNFC record page any locally added information should be prominent | Jitendra | 2015-09-22 | 2015-09-23
| Defect Closure (Sprint 1) | Shital and Web team | 2015-09-18 | 2015-09-21
| Automated unit testing completion for sprint 1 | Jitendra/ Abin/Shital | 2015-09-21 | 2015-09-29
| Interim release dates | Every alternate day starting 22 september
Note on F3: Sandarbh Sharma: Ian on leave from Wednesday