## Slide 1
RPS - Formulary Complete
Pending Work (MVP)

## Slide 2
Pending Work (MVP)
Tasks | Details | Remarks
Treatment summary page design | Display of Treatment Summary | Pending , development onshore, design to be completed offshore. Expected completion by Monday
User Authentication | NGINX integration, authentication based on IP, SSL etc. | Pending. To be completed next week.
Hide paediatric formulary (or adult) | Results from hidden formulary are not returned by the search on “All References” The formulary is not listed as available for the attachment of new drug records or local content. | Pending. 3 person days of work required, inclusive of testing post Authentication Need one day post completion of Authentication.
Guidance page design | Display for guidance | Pending, development onshore, design to be completed offshore. Expected completion by Tuesday

## Slide 3
Pending Work (MVP)
Tasks | Details | Remarks
Control of sequence of multiple-use notes within a given record | Reordering of Notes | Complete testing by Monday
Therapeutic context-dependent statuses | For Monographs. Display, Add, Amend and Delete | Complete testing by Monday
Home Page | Home Page, Notice Board, RSS Feeds, Branding, Logo management, Formulary Naming | 3 person days of work required, inclusive of testing post Authentication. Need one day post completion of Authentication.
Migration Activity (To be continued) | Customer data to be migrated from PostgreSQL to Elastic Search | Atul had completed work for Users, Formulary Status, Records. Remaining work to be done onshore by Nick.
Related information | Related information display and comparison | Complete testing by Tuesday

## Slide 4
Pending Work (MVP)
Tasks | Details | Remarks
View earlier versions when reviewing/editing | Compare versions | Complete testing by Tuesday
Web Formulary Report | Report | Not Started. Will be picked up as part of support activities
Rendering of wound care, borderline substances and interactions sections | Display for wound care, borderline substances and interactions sections | Pending , development onshore, design to be completed offshore Expected completion by Tuesday.
Notes to be marked “Public/Private” | Data to be saved in ES | Complete testing by Monday
UAT change | Issues identified on UAT testing | Need to be Fixed in parallel

## Slide 5
Sprint 7 – Retrospective
  What Worked
    Frequent check-ins, and prompt code reviews
    High level design approval from Ian.
  What can be improved
    Stable Development and test environment.
      Two separate environments being created on Cloud (Dev and QA)
    Questions on functionalities to be asked earlier in the sprint.