## Doc Info
Document |  | : | PRJ-CHK-033- Project Planing checklist
Issue |  | : | 1
Filename |  | : | PRJ-CHK-033- Project Planing checklist
Author |  | : | Rokshana K
Date |  | : | 2014-01-24
Revision History
Version No | Author |  | Approver | Release Date | Description of changes
1 | Rokshana K |  | Manisha Datar | 2014-01-24 | Created

## Checklist
Sr.No. | Process requirements | Contents | Required | Artefact | Comments
1 | Project Initiation | Contract, SOW, SORR, payment milestones, Billing type | Mandatory
2 | Project Scope | Items in current project scope,out of scope | Mandatory | Held in GitHub
3 | Critical success factors | Any crucial aspects absence of which can lead to project failure;eg. Absence of onshore product owner | Optional
4 | Service Level Agreements | If any, eg.turnaround time etc. | Optional
5 | Measurements | • Qualitative - CSS only for Customer Projects • Quantitative - Effort overrun, defect density • Any other project defined metrics (Productivity, utilization) please mention alongside | Mandatory
6 | Project Process | Refer to lifecycle checklist | Mandatory | https://github.com/sandarbhsharma/Project-Documents
7 | Project Resource Plan | • Resources roles & responsibilities • Team structure • H/w and s/w resources | Mandatory | Whizible Project Management --> Plan--> Resource Management | Available in Whizible under Project Management --> Plan--> Resource Management
8 | Governance & Escalation | • Monitoring at all levels of project lifecycle • Team communication plan • Reviews at defined intervals | Mandatory
9 | Quality Plan | Consists of - Audit Plan - Defect Prevention (RCA) - CAPA | Mandatory
10 | Risks Management Plan | Risk foreseen in project with respective impact on project success. Strategy to mitigate the same or contingency actions if the same is materialised | Mandatory | Whizible Project Management --> Plan--> Resource Management
11 | Configuration Management Plan | Details for maintaining integrity, confidentiality and avialability of documents for intended users. Change management process with baselining criteria. Retrival of required versions of documents if needed. A) For project process related artefacts | Mandatory | Others (Please specify) | GItHub
|  | B) For delivery artefacts | Mandatory | Others (Please specify) | GItHub
12 | Training Plan | Details of training required for team based on project requirement and respective assessment criateria | Mandatory |  | Since the project is a short term Training Plan is not applicable.
13 | Project standards | Naming convention, coding standards | Mandatory | https://github.com/sandarbhsharma/Project-Documents | Coding Standard document contains the necessary naming convention and coding standards required for the project.